## Main Plan
Schedule Digital Picking Systam Project (DPS Project)
| Place : MPC 93A1F | [22 empty] | Issue : K.Teerana
Date : 8 May 2018
Revise : 01
No | Detail |  | Respons | 2018 | [19 empty] | REMARK
|  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Input Part Order
| 1.1 CC-Link I/O Unit | AJ65SBTB1-32DT | Plan | [6 empty] | 2018-05-18
Action
| 1.2 BOX CONTROL | FB32 | Plan | [6 empty] | 2018-05-14
Action
| 1.3 Pushbutton Switch | AL6M-M14G | Plan | [6 empty] | 2018-05-14
Action
| 1.4 Sensor Cable | NASEU-23-4 | Plan |  | 2018-04-09
Action
| 1.5 Cable 3 Core | VCTF-A-0.3-3 | Plan |  | 2018-04-09
Action
| 1.6 Connector Housing | 1625-4P-50PS | Plan |  | 2018-04-09
Action
| 1.7 Connector Housing | 1625-4R-50PS | Plan |  | 2018-04-09
Action
| 1.8 Connector Housing | 1625-2P1-50PS | Plan |  | 2018-04-09
Action
| 1.9 Connector Housing | 1625-2R1-50PS | Plan |  | 2018-04-09
Action
| 1.10 Wiring Duct | WD-2525-4 | Plan |  |  |  |  | 2018-05-02
Action
| 1.11 Connector Pins | 1855TL | Plan |  | 2018-04-09
Action
| 1.12 Connector Pins | 1854TL | Plan |  | 2018-04-09
Action
| 1.13 CC-Link Cable | FANC-SB | Plan
Action
| 1.14 Cable 12 Core | VCTF-A-0.3-12 | Plan
Action
| 1.15 UN-INSULATED FORK TERMINAL | Y2-3 (BN-U3) | Plan
Action
| 1.16 Pushbutton Switch | A165E-S-02 | Plan
Action
2 | Reques inhouse
| 2.1 Box control DPS Project |  | Plan | [11 empty] | 2018-06-29
Action
| 2.3 Plate support cc-link |  | Plan | [11 empty] | 2018-06-29
Action
3 | Setup Project
| 3.1 Setup Machanics |  | Plan | [6 empty] | 2018-04-14 | [8 empty] | 2018-07-26
Action
| 3.2 Setup Electric |  | Plan
Action
| 3.3 Program |  | Plan
Action
| 3.4 Test Run |  | Plan
1 station = 1 week
Existing
Existing
Existing
Existing

## PRG.
Shooter no condo
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | 6 | 5 | 4 | 3 | 2 | 1 | 15 | 14 | 13 | 12 | 11 | 10
X |  | Orage | Sky | Pink | Green Light | Green | Yellow | Orange | Sky | Pink | Green Light | Whit | Black
Y |  | Black | Red | Whit | Gray | Blue | Brow | Orange | Sky | Pink | Green Light | Whit | Black
Input |  | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11
Output |  | M200 | M201 | M202 | M203 | M204 | M205 | M206 | M207 | M208 | M209 | M210 | M211
Input |  | M1105 | M1104 | M1103 | M1102 | M1101 | M1100 | M1114 | M1113 | M1112 | M1111 | M1110 | M1109
Output |  | M1305 | M1304 | M1303 | M1302 | M1301 | M1300 | M1314 | M1313 | M1312 | M1311 | M1310 | M1309
I/O | NO. | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  | 9 | 8 | 7 | 16 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 17
X |  | Green | Red | Gray | Brow | Red | Orange | Yellow | Green | Blue | Purple | Gray | Whit
Y |  | Green | Red | Gray | Black_Brow | Black_Red | Black_Orange | Black_Yellow | Black_Green | Black_Blue | Black_Purple | Black_Gray | Black_Whit
Input |  | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23
Output |  | M212 | M213 | M214 | M215 | M216 | M217 | M218 | M219 | M220 | M221 | M222 | M223
Input |  | M1108 | M1107 | M1106 | M1115 | M1124 | M1123 | M1122 | M1121 | M1120 | M1119 | M1118 | M1116
Output |  | M1308 | M1307 | M1306 | M1315 | M1324 | M1323 | M1322 | M1321 | M1320 | M1319 | M1318 | M1316
I/O | NO. | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 18 | 26 | 42 | 41 | 40
X |  | Brow | Red | Orange | Yellow | Green | Blue | Purple | Gray | Whit | Brow | Red | Orange
Y |  | Black_Brow | Black_Red | Black_Orange | Black_Yellow | Black_Green | Black_Blue | Black_Purple | Black_Gray | Black_Whit | Black_Brow | Black_Red | Black_Orange
Input |  | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35
Output |  | M224 | M225 | M226 | M227 | M228 | M229 | M230 | M231 | M232 | M233 | M234 | M235
Input |  | M1132 | M1131 | M1130 | M1129 | M1128 | M1127 | M1126 | M1117 | M1125 | M1141 | M1140 | M1139
Output |  | M1332 | M1331 | M1330 | M1329 | M1328 | M1327 | M1326 | M1317 | M1325 | M1341 | M1340 | M1339
I/O | NO. | 37 | 38 | 39 | 40 | 41 | 42
|  | 39 | 38 | 37 | 36 | 35 | 34
X |  | Yellow | Green | Blue | Purple | Gray | Whit
Y |  | Black_Yellow | Black_Green | Black_Blue | Black_Purple | Black_Gray | Black_Whit
Input |  | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47
Output |  | M236 | M237 | M238 | M239 | M240 | M241 | M242 | M243 | M244 | M245 | M246 | M247
Input |  | M1138 | M1137 | M1136 | M1135 | M1134 | M1133 | M1142 | M1143 | M1144 | M1145 | M1146 | M1147
Output |  | M1338 | M1337 | M1336 | M1335 | M1334 | M1333 | M1342 | M1343 | M1344 | M1345 | M1346 | M1347
Shooter no 19
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
|  |  | 1 | 3 | 5 | 9 | 10 | 11 | 12
X |  | Pink | Sky | Green Light | Orange | Gray | Red | Green | Black
Y |  | Whit | Yellow | Gray | Green | Blue | Green Light | Yellow | Whit
Input |  | M48 | M49 | M50 | M51 | M52 | M53 | M54 | M55
Output |  | M248 | M249 | M250 | M251 | M252 | M253 | M254 | M255
Input |  | M1162 | M1148 | M1150 | M1152 | M1156 | M1157 | M1158 | M1159
Output |  | M1362 | M1348 | M1350 | M1352 | M1356 | M1357 | M1358 | M1359
I/O | NO. | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  | 2 | 4 | 6 | 7 | 8 | 13 | 14
X |  | Pink | Sky | Green | Orange | Gray | Red | Green | Black
Y |  | Whit | Yellow | Pink | Sky | Orange | Red | Black | Brow
Input |  | M56 | M57 | M58 | M59 | M60 | M61 | M62 | M63
Output |  | M256 | M257 | M258 | M259 | M260 | M261 | M262 | M263
Input |  | M1163 | M1149 | M1151 | M1153 | M1154 | M1155 | M1160 | M1161
Output |  | M1363 | M1349 | M1351 | M1353 | M1354 | M1355 | M1360 | M1361
Shooter no 18
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
X |  | 2: Sky; 3: Pink; 4: Green Light; 5: Green
Y |  | 2: Gray; 3: Orange; 4: Red; 5: Yellow
Input |  | M64 | M65 | M66 | M67 | M68 | M69 | M70 | M71 | M72 | M73 | M74
Output |  | M264 | M265 | M266 | M267 | M268 | M269 | M270 | M271 | M272 | M273 | M274
Input |  | M1164 | M1165 | M1166 | M1167 | M1168 | M1169 | M1170 | M1171 | M1172 | M1173 | M1174
Output |  | M1364 | M1365 | M1366 | M1367 | M1368 | M1369 | M1370 | M1371 | M1372 | M1373 | M1374
Shooter no 17
I/O | NO. | bar: M64 M264 M1164 M1364
1
X | bar: M64 M264 M1164 M1364
Y | bar: M64 M264 M1164 M1364
Input |  | M64 M264 M1164 M1364: M75
Output |  | M64 M264 M1164 M1364: M275
Input |  | M64 M264 M1164 M1364: M1175
Output |  | M64 M264 M1164 M1364: M1375
Shooter no 16
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | 1 | 2 | 3 | 6 | 9 | 11 | 12 | 4 | 5 | 7 | 8 | 10 | 13 | 14
X |  | Green | Green Light | Sky | Gray | Brow | Red | Orange | Yellow | Green | Blue | Purple | Gray | Whit | Pink
Y |  | Orange | Yellow | Pink | Whit | Black_Brow | Black_Red | Black_Orange | Black_Yellow | Black_Green | Black_Blue | Black_Purple | Black_Gray | Black_Whit | Black_Pink
Input |  | M76 | M77 | M78 | M79 | M80 | M81 | M82 | M83 | M84 | M85 | M86 | M87 | M88 | M89
Output |  | M276 | M277 | M278 | M279 | M280 | M281 | M282 | M283 | M284 | M285 | M286 | M287 | M288 | M289
Input |  | M1176 | M1177 | M1178 | M1181 | M1184 | M1186 | M1187 | M1179 | M1180 | M1182 | M1183 | M1185 | M1188 | M1189
Output |  | M1376 | M1377 | M1378 | M1381 | M1384 | M1386 | M1387 | M1379 | M1380 | M1382 | M1383 | M1385 | M1388 | M1389
Shooter no 15
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
|  | 1 | 3 | 8 | 7 | 2 | 4 | 5 | 6
X |  | Orange | Sky | Pink | Green Light | Green | Yellow | Green Light | Green
Y |  | Gray | Blue | Brow | Red | Black | Whit | Yellow | Red
Input |  | M90 | M91 | M92 | M93 | M94 | M95 | M96 | M97
Output |  | M290 | M291 | M292 | M293 | M294 | M295 | M296 | M297
Input |  | M1190 | M1192 | M1197 | M1196 | M1191 | M1195 | M1194 | M1195
Output |  | M1390 | M1392 | M1397 | M1396 | M1391 | M1395 | M1394 | M1395
Shooter no 14
I/O | NO. | M90 M290: 1; M91 M291: 2; M92 M292: 3
|  | 1 | 2 | 3
X |  | M90 M290: Pink; M91 M291: Sky; M92 M292: Orage
Y |  | M90 M290: Black; M91 M291: Whit; M92 M292: Gray
Input |  | M90 M290: M98; M91 M291: M99; M92 M292: M100
Output |  | M90 M290: M298; M91 M291: M299; M92 M292: M300
Input |  | M90 M290: M1198; M91 M291: M1199; M92 M292: M1200
Output |  | M90 M290: M1398; M91 M291: M1399; M92 M292: M1400
Shooter no 13
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | 1 | 2 | 3 | 4 | 8 | 7 | 6 | 5 | 9 | 10 | 11 | 12 | 13 | 14
X |  | Orage | Sky | Pink | Green | Orage | Sky | Pink | Green | Orange | Sky | Sky | Green | Yellow | Brow
Y |  | Gray | Whit | Black | Red | Gray | Whit | Black | Red | gray | Whit | Black | Red | Green Light | Blue
Input |  | M101 | M102 | M103 | M104 | M105 | M106 | M107 | M108 | M109 | M110 | M111 | M112 | M113 | M114
Output |  | M301 | M302 | M303 | M304 | M305 | M306 | M307 | M308 | M309 | M310 | M311 | M312 | M313 | M314
Input |  | M1201 | M1202 | M1203 | M1204 | M1208 | M1207 | M1206 | M1205 | M1209 | M1210 | M1211 | M1212 | M1213 | M1214
Output |  | M1401 | M1402 | M1403 | M1404 | M1408 | M1407 | M1406 | M1405 | M1409 | M1410 | M1411 | M1412 | M1413 | M1414
Shooter no 12
I/O | NO. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | 1 | 4 | 6 | 8 | 10 | 2 | 3 | 5 | 7 | 9 | 11
X |  | Whit | Orange | Sky | Red | Green Light | Whit | Green Light | Brow | Red | Orange | Sky
Y |  | Black | Gray | Pink | Yellow | Green | Black | Green | Blue | Yellow | Gray | Pink
Input |  | M115 | M116 | M117 | M118 | M119 | M120 | M121 | M122 | M123 | M124 | M125 | M126 | M127
Output |  | M315 | M316 | M317 | M318 | M319 | M320 | M321 | M322 | M323 | M324 | M325 | M326 | M327
Input |  | M1215 | M1218 | M1220 | M1222 | M1224 | M1216 | M1217 | M1219 | M1221 | M1223 | M1225 | M1226 | M1227
Output |  | M1415 | M1418 | M1420 | M1422 | M1424 | M1416 | M1417 | M1419 | M1421 | M1423 | M1425 | M1426 | M1427
|  | NO | Color CC-Link
1
2
3
4
5
6
7
8

## 1
No. | IO | X | Y | Input | Input1 | Output | Output1 | Shooter | D75 | D76 | D77 | D78 | E38 | E39 | E40
1 | 6 | Brow | Yellow | M5 | M1100 | M1300 | M205 | condeo | bar: D75; E39
2 | 5 | Blue | Green | M4 | M1101 | M1301 | M204 | condeo | bar: D76 to D77; E38
3 | 4 | Gray | Green Light | M3 | M1102 | M1302 | M203 | condeo | bar: D75 to E40
4 | 3 | Whit | Pink | M2 | M1103 | M1303 | M202 | condeo | bar: E40
5 | 2 | Red | Sky | M1 | M1104 | M1304 | M201 | condeo | bar: D78
6 | 1 | Black | Orage | M0 | M1105 | M1305 | M200 | condeo | bar: D75 to E40
7 | 15 | Gray | Gray | M14 | M1106 | M1306 | M214 | condeo | bar: D75 to E40
8 | 14 | Red | Red | M13 | M1107 | M1307 | M213 | condeo | bar: D75 to E40
9 | 13 | Green | Green | M12 | M1108 | M1308 | M212 | condeo | bar: D75 to E40
10 | 12 | Black | Black | M11 | M1109 | M1309 | M211 | condeo | bar: D75 to E40
11 | 11 | Whit | whit | M10 | M1110 | M1310 | M210 | condeo | bar: D75 to E40
12 | 10 | Green Light | Green Light | M9 | M111 | M1311 | M209 | condeo | bar: D75 to E40
13 | 9 | Pink | Pink | M8 | M1112 | M1312 | M208 | condeo | bar: D75 to E40
14 | 8 | Sky | Sky | M7 | M113 | M1313 | M207 | condeo | bar: D75 to E40
15 | 7 | Orange | Orage | M6 | M1114 | M1314 | M206 | condeo | bar: E38 to E40
16 | 16 | Brow | Black Brow | M1315 | M15 | M215 | M1115 | condeo | bar: D75 to D78
17 | 17 | Whit | Black Whit | M1316 | M23 | M223 | M1116 | condeo | bar: E38 to E40
18 | 32 | Gray | Black Gray | M1317 | M31 | M231 | M1117 | condeo | bar: D75 to D78
19 | 23 | Gray | Black Gray | M1318 | M22 | M222 | M1118 | condeo | bar: D75 to E40
20 | 22 | Purple | Black Purple | M1319 | M21 | M221 | M1119 | condeo | bar: D76 to D77
21 | 21 | Blue | Black Blue | M1320 | M20 | M220 | M1120 | condeo | bar: D78 to E38
22 | 20 | Green | Black Green | M1321 | M19 | M219 | M1121 | condeo | bar: E39
23 | 19 | Yellow | Black Yellow | M1322 | M18 | M218 | M1122 | condeo | bar: D75
24 | 18 | Orange | Black Orange | M1323 | M17 | M217 | M1123 | condeo | bar: E40
25 | 17 | Red | Black Red | M1324 | M16 | M216 | M1124 | condeo | bar: D75 to E40
26 | 33 | Whit | Black Whit | M1325 | M32 | M232 | M1125 | condeo | bar: D75 to E40
27 | 31 | Purple | Black Purple | M1326 | M30 | M230 | M1126 | condeo | bar: D75 to E40
28 | 30 | Blue | Black Blue | M1327 | M29 | M229 | M1127 | condeo | bar: D75 to E40
29 | 29 | Green | Black Green | M1328 | M28 | M228 | M1128 | condeo | bar: D75 to D78
30 | 28 | Yellow | Black Yellow | M1329 | M27 | M227 | M1129 | condeo | bar: D75 to E40
31 | 27 | Orange | Black Orange | M1330 | M26 | M226 | M1130 | condeo | bar: D75 to E40
32 | 26 | Red | Black Red | M1331 | M25 | M225 | M1131 | condeo | bar: D75 to E40
33 | 25 | Brow | Black Brow | M1332 | M24 | M224 | M1132 | condeo | bar: D75 to E40
34 | 42 | Whit | Black Whit | M1333 | M41 | M241 | M1133 | condeo | bar: D75 to E40
35 | 41 | Gray | Black Gray | M1334 | M40 | M240 | M1134 | condeo | bar: D75 to E40
36 | 40 | Purple | Black Purple | M1335 | M39 | M239 | M1135 | condeo | bar: D75 to E40
37 | 39 | Blue | Black Blue | M1336 | M38 | M238 | M1136 | condeo | bar: D75 to E40
38 | 38 | Green | Black Green | M1337 | M37 | M237 | M1137 | condeo | bar: D75 to E40
39 | 37 | Yellow | Black Yellow | M1338 | M36 | M236 | M1138 | condeo | bar: D75 to E40
40 | 36 | Orange | Black Orange | M1339 | M35 | M235 | M1139 | condeo | bar: E38 to E40
41 | 35 | Red | Black Red | M1340 | M34 | M234 | M1140 | condeo | bar: D75 to D78
42 | 34 | Brow | Black Brow | M1341 | M33 | M233 | M1141 | condeo | bar: D75 to E40
43 |  |  |  | M1342 | M42 | M242 | M1142 | condeo
44 |  |  |  | M1343 | M43 | M243 | M1143 | condeo
45 |  |  |  | M1344 | M44 | M244 | M1144 | condeo
46 |  |  |  | M1345 | M45 | M245 | M1145 | condeo
47 |  |  |  | M1346 | M46 | M246 | M1146 | condeo
48 |  |  |  | M1347 | M47 | M247 | M1147 | condeo
1 | 2 | Sky | Yellow | M1348 | M49 | M249 | M1148 | 19 | bar: D75 to D78
2 | 10 | Sky | Yellow | M1349 | M57 | M257 | M1149 | 19 | bar: D75 to D78
3 | 3 | Green Light | Gray | M1350 | M50 | M250 | M1150 | 19 | bar: D75 to D78
4 | 11 | Green | Pink | M1351 | M58 | M258 | M1151 | 19 | bar: D75 to D78
5 | 4 | Orange | Green | M1352 | M51 | M251 | M1152 | 19 | bar: D75 to D78
6 | 12 | Orange | Sky | M1353 | M59 | M259 | M1153 | 19 | bar: D75 to D78
7 | 13 | Gray | Orange | M1354 | M60 | M260 | M1154 | 19 | bar: D75 to D78
8 | 14 | Red | Red | M1355 | M61 | M261 | M1155 | 19 | bar: D75 to D78
9 | 5 | Gray | Blue | M1356 | M52 | M252 | M1156 | 19 | bar: D75 to E40
10 | 6 | Red | Green Light | M1357 | M53 | M253 | M1157 | 19 | bar: D78
11 | 7 | Green | Yellow | M1358 | M54 | M254 | M1158 | 19 | bar: D75
12 | 8 | Black | Whit | M1359 | M55 | M255 | M1159 | 19 | bar: D75; E39 to E40
13 | 15 | Green | Black | M1360 | M62 | M262 | M1160 | 19 | bar: D75 to E40
14 | 16 | Black | Brow | M1361 | M63 | M263 | M1161 | 19 | bar: D75 to E40
15 | 1 | Pink | Whit | M1362 | M48 | M248 | M1162 | 19
16 | 9 | Pink | Whit | M1363 | M56 | M256 | M1163 | 19
1 | 1 |  |  | M1364 | M64 | M264 | M1164 | 18 | bar: D76 to D77; E38
2 | 2 | Sky | Gray | M1365 | M65 | M265 | M1165 | 18 | bar: D76 to D78
3 | 3 | Pink | Orange | M1366 | M66 | M266 | M1166 | 18 | bar: D75 to E40
4 | 4 | Green Light | Red | M1367 | M67 | M267 | M1167 | 18 | bar: D75 to E40
5 | 5 | Green | Yellow | M1368 | M68 | M268 | M1168 | 18 | bar: D75 to E40
6 | 6 |  |  | M1369 | M69 | M269 | M1169 | 18 | bar: D75 to E40
7 | 7 |  |  | M1370 | M70 | M270 | M1170 | 18 | bar: D75 to E40
8 | 8 |  |  | M1371 | M71 | M271 | M1171 | 18 | bar: D75 to E40
9 | 9 |  |  | M1372 | M72 | M272 | M1172 | 18 | bar: D75 to E40
10 | 10 |  |  | M1373 | M73 | M273 | M1173 | 18 | bar: D75 to E40
11 | 11 |  |  | M1374 | M74 | M274 | M1174 | 18 | bar: D75 to E40
1 | 1 |  |  | M1375 | M75 | M275 | M1175 | 17 | bar: D75 to E40
1 | 1 | Green | Orange | M1376 | M76 | M276 | M1176 | 16 | bar: D75 to E40
2 | 2 | Green Light | Yellow | M1377 | M77 | M277 | M1177 | 16 | bar: D75 to E40
3 | 3 | Sky | Pink | M1378 | M78 | M278 | M1178 | 16 | bar: D75 to D78
4 | 6 | Gray | Whit | M1379 | M79 | M279 | M1179 | 16 | bar: D75 to E40
5 | 9 | Brow | Black Brow | M1380 | M80 | M280 | M1180 | 16 | bar: D75 to D78
6 | 11 | Red | Black Red | M1381 | M81 | M281 | M1181 | 16 | bar: E38 to E40
7 | 12 | Orange | Black Orange | M1382 | M82 | M282 | M1182 | 16 | bar: E38 to E40
8 | 4 | Yellow | Black Yellow | M1383 | M83 | M283 | M1183 | 16 | bar: E38 to E40
9 | 5 | Green | Black Green | M1384 | M84 | M284 | M1184 | 16 | bar: E38 to E40
10 | 7 | Blue | Black Blue | M1385 | M85 | M285 | M1185 | 16 | bar: E38 to E40
11 | 8 | Purple | Black Purple | M1386 | M86 | M286 | M1186 | 16 | bar: E38 to E40
12 | 10 | Gray | Black Gray | M1387 | M87 | M287 | M1187 | 16 | bar: E38 to E40
13 | 13 | Whit | Black Whit | M1388 | M88 | M288 | M1188 | 16 | bar: E38 to E40
14 | 14 | Pink | Black Pink | M1389 | M89 | M289 | M1189 | 16 | bar: E38 to E40
1 | 1 | Orange | Gray | M1390 | M90 | M290 | M1190 | 15 | bar: E38 to E40
2 | 3 | Sky | Blue | M1391 | M91 | M291 | M1191 | 15 | bar: E38 to E40
3 | 8 | Pink | Brow | M1392 | M92 | M292 | M1192 | 15 | bar: E38 to E40
4 | 7 | Green Light | Red | M1393 | M93 | M293 | M1193 | 15 | bar: E38 to E40
5 | 2 | Green | Black | M1394 | M94 | M294 | M1194 | 15 | bar: E38 to E40
6 | 4 | Yellow | Whit | M1395 | M95 | M295 | M1195 | 15 | bar: E38 to E40
7 | 5 | Green Light | Yellow | M1396 | M96 | M296 | M1196 | 15 | bar: E38 to E40
8 | 6 | Green | Red | M1397 | M97 | M297 | M1197 | 15 | bar: E38 to E40
1 | 1 | Pink | Black | M1398 | M98 | M298 | M1198 | 14 | bar: D75 to E40
2 | 2 | Sky | Whit | M1399 | M99 | M299 | M1199 | 14 | bar: D75 to D78
3 | 3 | Orange | Gray | M1400 | M100 | M300 | M1200 | 14 | bar: D75 to E40
1 | 1 | Orange | Gray | M1401 | M101 | M301 | M1201 | 13 | bar: D75 to D78
2 | 2 | Sky | Whit | M1402 | M102 | M302 | M1202 | 13 | bar: D75 to D78
3 | 3 | Pink | Black | M1403 | M103 | M303 | M1203 | 13 | bar: D75 to D78
4 | 4 | Green | Red | M1404 | M104 | M304 | M1204 | 13 | bar: D75 to D78
5 | 8 | Orange | Gray | M1405 | M105 | M305 | M1205 | 13 | bar: D75 to D78
6 | 7 | Sky | Whit | M1406 | M106 | M306 | M1206 | 13 | bar: D75 to D78
7 | 6 | Pink | Black | M1407 | M107 | M307 | M1207 | 13 | bar: D75 to E40
8 | 5 | Green | Red | M1408 | M108 | M308 | M1208 | 13 | bar: D75 to E40
9 | 9 | Orange | Gray | M1409 | M109 | M309 | M1209 | 13 | bar: D75 to E40
10 | 10 | Sky | Whit | M1410 | M110 | M310 | M1210 | 13 | bar: D75 to E40
11 | 11 | Sky | Black | M1411 | M111 | M311 | M1211 | 13 | bar: D75 to D77; E38 to E40
12 | 12 | Green | Red | M1412 | M112 | M312 | M1212 | 13 | bar: D75 to D78
13 | 13 | Yellow | Green Light | M1413 | M113 | M313 | M1213 | 13 | bar: D75 to E40
14 | 14 | Brow | Blue | M1414 | M114 | M314 | M1214 | 13 | bar: D75 to D78
1 | 1 | Whit | Black | M1415 | M115 | M315 | M1215 | 12 | bar: E38 to E39
2 | 4 | Orange | Gray | M1416 | M116 | M316 | M1216 | 12 | bar: D75 to E40
3 | 6 | Sky | Pink | M1417 | M117 | M317 | M1217 | 12 | bar: D75 to E40
4 | 8 | Red | Yellow | M1418 | M118 | M318 | M1218 | 12 | bar: D75 to D78
5 | 10 | Green Light | Green | M1419 | M119 | M319 | M1219 | 12 | bar: D75
6 | 2 | Whit | Black | M1420 | M120 | M320 | M1220 | 12 | bar: D75
7 | 3 | Green Light | Green | M1421 | M121 | M321 | M1221 | 12 | bar: D76 to D77
8 | 5 | Brow | Blue | M1422 | M122 | M322 | M1222 | 12 | bar: D76 to D77
9 | 7 | Red | Yellow | M1423 | M123 | M323 | M1223 | 12 | bar: D78
10 | 9 | Orange | Gray | M1424 | M124 | M324 | M1224 | 12 | bar: D78
11 | 11 | Sky | Pink | M1425 | M125 | M325 | M1225 | 12 | bar: E40
12 |  |  |  | M1426 | M126 | M326 | M1226 | 12
13 |  |  |  | M1427 | M127 | M327 | M1227 | 12